## Lists
Status | Owner | Blocker | Priority
Not Started | Agency | Yes | Critical
Waiting on Client | Client | No | High
Blocked | Agency + Client | Conditional | Medium
In Progress | Tech Team |  | Low
Internal Review | Automation Team
Ready for QA | Compliance
Needs Fix | Billing
Completed | Sales
Not Applicable | Support
Project Lead
Third Party

## DASHBOARD
BES CRM Full Infrastructure Build Tracker
Project | Client | Start Date | Target Go-Live | Build Window | Support Window | Project Lead | Status
GHL Full Infrastructure Build |  |  |  | 30-45 days | 3 months |  | Not Started
Phase | Target Window | Total Tasks | Completed | Blocked/Waiting | % Complete
PHASE 0 - ACCESS & LOCK | Day 0-5 | 24 | 0 | 14 | 0%
PHASE 1 - FOUNDATION | Day 5-18 | 39 | 0 | 0 | 0%
PHASE 2 - AUTOMATIONS | Day 15-30 | 30 | 0 | 0 | 0%
PHASE 3 - INTEGRATIONS | Day 25-38 | 18 | 0 | 0 | 0%
PHASE 4 - OPTIMIZATION | Day 35-45 | 12 | 0 | 0 | 0%
PHASE 5 - QA & DELIVERY | Final QA Day 38-45 | 17 | 0 | 0 | 0%
Strategic Build Standard
This tracker is built for full GHL business infrastructure projects, not snapshot installs. Use it to manage 30-45 day builds for credit repair, business funding, commercial funding, business acquisition, business setup assistance, real estate/broker, tax preparer, coaching, education, and related regulated or compliance-sensitive business niches. Phase 5 is QA/delivery, and the 3-month support period should begin after final delivery/sign-off.

## PHASE 0 - ACCESS & LOCK
PHASE 0 - ACCESS & LOCK
Phase | Section | Task | Details / Acceptance Criteria | Owner | Blocker | Priority | Due Date | Status | Document Link | Client Note | Dee's Note | Team's Remarks
Phase 0 | Internal Setup | Create internal project folder | Create structured project folder with intake, access, compliance, assets, build, testing, delivery, support, and archive folders. | Agency | No | Critical |  | Not Started
Phase 0 | Internal Setup | Create client asset folder | Create shared/client-facing folder for logos, copy, policies, voice notes, references, screenshots, and brand files. | Agency | No | High |  | Not Started
Phase 0 | Internal Setup | Create access tracker | Set up tracker for GHL, domain, DNS, email admin, payments, Zapier/Pabbly, ManyChat, social, Drive, ad accounts, pixels, and existing CRM. | Agency | No | Critical |  | Not Started
Phase 0 | Internal Setup | Create compliance tracker | Track privacy, terms, refund, cancellation, SMS consent, email unsubscribe, call recording, credit repair disclosures, funding disclaimers, approved/prohibited claims. | Agency | No | Critical |  | Not Started
Phase 0 | Internal Setup | Create build checklist | Create master tracker for all phases, owners, blockers, dependencies, due dates, QA, and sign-off. | Agency | No | Critical |  | Not Started
Phase 0 | Internal Setup | Create revision tracker | Track revisions, bug fixes, out-of-scope requests, approval status, and completion. | Agency | No | Medium |  | Not Started
Phase 0 | Internal Setup | Create blocker tracker | Track blockers, owner, severity, due date, workaround, and resolution status. | Agency | No | Critical |  | Not Started
Phase 0 | Internal Setup | Create workflow map | Prepare workflow map for lead capture, booking, onboarding, funding, credit repair lifecycle, billing, compliance holds, and support. | Agency | No | High |  | Not Started
Phase 0 | Internal Setup | Create pipeline map | Map all required pipelines and stages before building. | Agency | No | High |  | Not Started
Phase 0 | Client Inputs | Collect legal business name and DBA | Confirm legal entity, DBA/public brand, authorized representative, and owner. | Client | Yes | Critical |  | Waiting on Client
Phase 0 | Client Inputs | Collect business contact and operating info | Collect address, timezone, currency, support email, support phone, business hours, holiday hours, service areas, and niche category. | Client | Yes | Critical |  | Waiting on Client
Phase 0 | Client Inputs | Collect team roster and role assignments | Collect sales, funding advisor, fulfillment, billing, compliance, support, admin, and VA ownership rules. | Client | Yes | Critical |  | Waiting on Client
Phase 0 | Offer Strategy | Collect current offers and pricing | Collect offer name, price, billing method, payment timing, refund rules, cancellation rules, delivery method, eligibility, required docs, disclosures, included/not included. | Client | Yes | Critical |  | Waiting on Client
Phase 0 | Offer Strategy | Collect rough offer ideas if final offers do not exist | Accept notes, screenshots, voice notes, Google Docs, old funnels, references, draft pricing, and manual process explanations. | Client | Conditional | High |  | Waiting on Client
Phase 0 | Compliance Direction | Collect policy URLs or rules | If privacy/terms/refund/service agreement URLs do not exist, collect current rules and preferences so BES can structure placeholders/pages. | Client | Yes | Critical |  | Waiting on Client
Phase 0 | Compliance Direction | Collect credit repair compliance direction | Agreement template, disclosures, Consumer Credit File Rights Notice, cancellation language, payment rules, onboarding requirements, consent language, ESIGN language if used. | Client | Conditional | Critical |  | Waiting on Client
Phase 0 | Compliance Direction | Collect funding compliance direction | Funding disclosure, eligibility rules, no guarantee language, broker disclosure if applicable, application disclaimers, follow-up messaging rules. | Client | Conditional | Critical |  | Waiting on Client
Phase 0 | Access | Collect GHL owner/admin access | Owner/Admin access strongly preferred for full infrastructure build. Limited access can delay or block configuration. | Client | Yes | Critical |  | Waiting on Client
Phase 0 | Access | Collect domain/DNS access | Registrar or DNS access required for domain, SSL, email authentication, tracking domains, and funnel connection. | Client | Yes | Critical |  | Waiting on Client
Phase 0 | Access | Collect email admin access | Google Workspace/Microsoft 365 or provider admin access required for branded email, SPF, DKIM, DMARC, reply-to setup. | Client | Conditional | High |  | Waiting on Client
Phase 0 | Access | Collect payment processor access if included | Stripe/Authorize/PayPal or other processor access required if payments, invoices, subscriptions, or payment workflows are in scope. | Client | Conditional | High |  | Waiting on Client
Phase 0 | Access | Collect integration access if included | Zapier/Pabbly, DisputeFox, ManyChat, Google Drive/Dropbox/OneDrive, social channels, ad accounts, pixels, existing CRM. | Client | Conditional | High |  | Waiting on Client
Phase 0 | Brand Assets | Collect brand assets or preferences | Logo, favicon, colors, fonts, photos, copy, testimonials, disclaimers, social links, screenshots, references. If missing, collect style preferences. | Client | Conditional | Medium |  | Waiting on Client
Phase 0 | Strategy Lock | Approve build architecture | Confirm scope, pipeline structure, entry points, offers, compliance rules, payment rules, SMS rules, integrations, and phase plan before heavy build. | Agency + Client | Yes | Critical |  | Not Started

## PHASE 1 - FOUNDATION
PHASE 0 - ACCESS & LOCK
Phase | Section | Task | Details / Acceptance Criteria | Owner | Blocker | Priority | Due Date | Status | Document Link | Client Note | Dee's Note | Team's Remarks
Phase 1 | Core Infrastructure | Create/verify GHL sub-account | Sub-account exists and is assigned to correct agency/client environment. | Tech Team | No | Critical |  | Not Started
Phase 1 | Core Infrastructure | Complete Business Profile | Company name, legal name, address, support email, support phone, website, timezone, currency, category, logo, and hours completed. | Tech Team | Yes | Critical |  | Not Started
Phase 1 | Core Infrastructure | Configure business hours and after-hours baseline | True operating hours configured. Holiday hours documented if applicable. After-hours logic documented. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Core Infrastructure | Configure role-based users and permissions | Admin, Sales, Funding Advisor, Credit Specialist, Fulfillment, Billing, Compliance, Support, VA roles created and restricted. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Core Infrastructure | Test user permissions by role | Log in/test each role. Confirm sales no settings, fulfillment no billing, billing no workflows, support no delete, exports restricted. | Tech Team | No | High |  | Not Started
Phase 1 | Core Infrastructure | Configure contact deduplication | Duplicate by email/phone, merge strategy, owner preservation, workflow restart prevention, manual duplicate review process. | Tech Team | No | High |  | Not Started
Phase 1 | Core Infrastructure | Configure opportunity defaults | Default pipeline, default stage, fallback owner, source tracking, won/lost reasons, opportunity naming format. | Tech Team | No | High |  | Not Started
Phase 1 | Core Infrastructure | Create custom values | Legal name, DBA, support email/phone, address, website, policy URLs, booking links, offer names, social links, business hours, footer, SMS help/opt-out. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Core Infrastructure | Create custom fields - contact level | Preferred language, credit goal, score range, state, consent fields, agreement dates, cooling-off, plan terms, DNC reason, lead source, UTM, service type, intake channel, identity verified, risk flag, external links. | Tech Team | No | Critical |  | Not Started
Phase 1 | Core Infrastructure | Create custom fields - opportunity level | Program type, requested amount, revenue range, years in business, docs dates, lender submission date, terms date, funded date, disqualification reason, deal temperature, advisor, hold reason, manual billing, stage dates. | Tech Team | No | Critical |  | Not Started
Phase 1 | Core Infrastructure | Create tag library | Lead, status, compliance, billing, workflow, source, team, and risk tags created using clean naming conventions. | Tech Team | No | Critical |  | Not Started
Phase 1 | Domain & SSL | Connect primary domain | Add main website/root domain in GHL or configure appropriate subdomain approach. | Tech Team | Yes | Critical |  | Not Started
Phase 1 | Domain & SSL | Connect funnel domain | Configure funnel domain/subdomain and set as default funnel domain where applicable. | Tech Team | Yes | Critical |  | Not Started
Phase 1 | Domain & SSL | Configure tracking domain | Set branded tracking domain if email/link tracking is included. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Domain & SSL | Verify DNS and SSL | DNS records verified, SSL active, HTTPS enforced, no redirect loops, propagation checked. | Tech Team | Yes | Critical |  | Not Started
Phase 1 | Domain & SSL | Create branded 404 page | 404 page created, assigned, and tested with random URL. | Tech Team | No | Medium |  | Not Started
Phase 1 | Email Foundation | Connect branded email domain | Business email matches branded domain. No personal Gmail/Yahoo/Outlook sender in production unless temporary/startup exception. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Email Foundation | Configure sending domain authentication | Dedicated sending domain, SPF, DKIM, DMARC, reply-to, from address, tracking domain, email footer, unsubscribe link. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Email Foundation | Document email warm-up rules | Low send limits, no bulk sends during warm-up, segmented sending, suppression behavior, bounce/spam complaint suppression. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Phone & SMS Readiness | Purchase/connect phone number | LC Phone/GHL-native number, local vs toll-free decision, correct country, assigned to sub-account/users, default outbound number. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Phone & SMS Readiness | Configure call routing baseline | Inbound routing, outbound caller ID, voicemail, missed-call text-back, after-hours routing, fallback routing. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Phone & SMS Readiness | Submit A2P/TFN where required | A2P brand/campaign registration or toll-free verification submitted with website, privacy, terms, opt-in description, samples, use case. | Agency + Client | Conditional | Critical |  | Not Started
Phase 1 | Website Build | Build corporate website pages | Home, How It Works, Services, About, FAQ, Schedule Consultation, Contact, disclosures, cancellation, privacy, terms, funding/no-guarantee pages as applicable. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Website Build | Configure page technical requirements | Meta title, meta description, OG image, basic schema if applicable, pixels/GA4 if included, mobile optimization, footer disclosures. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Funnel Build | Build lead capture funnel | Landing page, form, thank-you page, calendar or next step, tracking, hidden fields, pipeline trigger. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Funnel Build | Build credit consultation funnel if applicable | Credit consultation page, booking/lead form, disclaimer placement, thank-you/confirmation page. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Funnel Build | Build funding/commercial funding funnel if applicable | Funding page, intake/application form, no-guarantee language, document/booking CTA, thank-you page. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Funnel Build | Build clarity/business setup/education funnel if applicable | Clarity call, business setup, acquisition, tax, real estate/broker, mentorship or related offer entry point. | Tech Team | Conditional | Medium |  | Not Started
Phase 1 | Forms & Intake | Build universal consultation form | Hidden UTM fields, SMS/email consent, consent version, service type, lead source, owner assignment, opportunity creation. | Tech Team | No | Critical |  | Not Started
Phase 1 | Forms & Intake | Build service-specific intake forms | Credit repair, funding, commercial funding, business acquisition, setup assistance, real estate/broker, tax, clarity call as applicable. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Forms & Intake | Build operations forms | Onboarding packet, secure document upload, cancellation request, client update submission, complaint/escalation form. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Calendar Setup | Create calendars | Consultation, credit consultation, funding consultation, business setup, clarity call, onboarding, support as applicable. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Calendar Setup | Configure calendar sync and conflict prevention | Google/Outlook sync, availability, buffers, minimum notice, round robin, confirmation page, reminders connection. | Tech Team | Conditional | High |  | Not Started
Phase 1 | Pipelines | Create Credit Repair Sales Intake pipeline | Stages: New Lead, Contact Attempted, Consultation Scheduled, Consultation Completed, Qualified/Agreement Sent, Agreement Signed, Cooling-Off, Ready for Invoice, Agreement Expired, Not Qualified, Cancelled, Compliance Hold. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Pipelines | Create Credit Repair Active Lifecycle pipeline | Stages: Onboarding Pending, Onboarding Complete, Round 1-6 Sent, Monitoring, Completed, Cancelled, Archived, Compliance Hold. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Pipelines | Create Business Funding pipeline | Stages: New Lead, Docs Requested, Docs Received, Submitted to Lender, Terms Received, Funded, Not Qualified, Nurture. | Tech Team | Conditional | Critical |  | Not Started
Phase 1 | Pipelines | Create Clarity/Education pipeline | Stages: Booked, Attended, Follow-Up, Converted, Nurture. | Tech Team | Conditional | Medium |  | Not Started
Phase 1 | Pipelines | Create Support/Risk pipeline | Stages: New Support Request, Billing Issue, Technical Issue, Document Issue, Complaint, Refund Request, Attorney Mention, Compliance Review, Resolved, Closed. | Tech Team | No | High |  | Not Started
Phase 1 | Lead Automation | Build basic lead capture routing | Form submission creates/updates contact, applies tags/fields, creates opportunity, assigns owner, sends internal alert, triggers confirmation email/SMS if compliant. | Automation Team | No | Critical |  | Not Started

## PHASE 2 - AUTOMATIONS
PHASE 2 - AUTOMATIONS
Phase | Section | Task | Details / Acceptance Criteria | Owner | Blocker | Priority | Due Date | Status | Document Link | Client Note | Dee's Note | Team's Remarks
Phase 2 | Intake & Routing | Build speed-to-lead workflow | Immediate lead routing, owner assignment, internal notification, first response email/SMS if allowed. | Automation Team | No | Critical |  | Not Started
Phase 2 | Intake & Routing | Build service type tagging workflow | Apply service tags based on form, funnel, chat, calendar, ManyChat, or manual selection. | Automation Team | No | High |  | Not Started
Phase 2 | Intake & Routing | Build business hours and after-hours logic | Route leads differently during open/closed hours. Create callback tasks after hours. | Automation Team | No | High |  | Not Started
Phase 2 | Phone/SMS | Build inbound call workflow | Inbound call logs, assigns owner, creates task/notification, updates conversation. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Phone/SMS | Build missed call workflow | Compliance-safe missed-call text-back, callback task, owner notification, after-hours handling. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Phone/SMS | Build STOP/DNC handler | Detect STOP/CANCEL/UNSUBSCRIBE, apply DND/DNC, stop active workflows, close conversation, create internal log. | Automation Team | No | Critical |  | Not Started
Phase 2 | Phone/SMS | Build HELP response | Compliant HELP auto-response with business identity/support contact. | Automation Team | No | High |  | Not Started
Phase 2 | Credit Repair Sales | Build booking confirmation workflow | Email/SMS confirmation if compliant, stage movement, internal notification. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Credit Repair Sales | Build appointment reminders | 24h and 1h reminders, SMS only with consent and approval, email fallback. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Credit Repair Sales | Build no-show recovery | No-show stage movement, reschedule follow-up, task, nurture if no response. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Credit Repair Sales | Build consultation outcome routing | Routes qualified, not qualified, agreement sent, nurture, compliance hold, or cancelled outcomes. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Credit Repair Sales | Build agreement sent/viewed/signed workflows | Agreement reminders, status fields, stage movement, notifications, and next step logic. | Automation Team | Conditional | Critical |  | Not Started
Phase 2 | Credit Repair Sales | Build cooling-off enforcement | Track cooling-off start/end dates and prevent billing/fulfillment advancement until approved timing rules are met. | Automation Team | Conditional | Critical |  | Not Started
Phase 2 | Credit Repair Sales | Build manual billing authorization trigger | Manual billing safeguard for credit repair compliance. No automated charge unless client rules approve. | Automation Team | Conditional | Critical |  | Not Started
Phase 2 | Credit Repair Active | Build pipeline transfer to active lifecycle | Move from agreement/client-ready status into active lifecycle pipeline with onboarding status. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Credit Repair Active | Build onboarding packet reminders | Send onboarding request, follow-up reminders, incomplete onboarding tasks, document status updates. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Credit Repair Active | Build credit monitoring issue workflow | Applies issue status, creates task, sends approved instructions, pauses related processing where required. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Credit Repair Active | Build round advancement workflow | Round 1-6 status movement, internal reminders, client update, archive/completed pathway. | Automation Team | Conditional | Medium |  | Not Started
Phase 2 | Credit Repair Active | Build cancellation and archive workflow | Cancellation processing, stop workflows, update stages, archive automation. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Funding | Build funding consultation reminder | Email/SMS if allowed, advisor alert, stage movement. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Funding | Build document request automation | Docs requested, reminder sequence, internal task, docs received update. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Funding | Build lender submission/status workflows | Submitted to lender, terms received, funded, not qualified, nurture, closed follow-up. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Clarity/Education | Build clarity/education booking and follow-up | Booking confirmation, reminder sequence, post-call follow-up, upgrade trigger, nurture. | Automation Team | Conditional | Medium |  | Not Started
Phase 2 | Chat & Conversations | Create and embed web chat widget | Widget embedded sitewide with service selection prompt, consent language, hours logic. | Automation Team | Conditional | Medium |  | Not Started
Phase 2 | Chat & Conversations | Build chat routing workflows | Auto-tag, assign owner, create pipeline opportunity, missed chat follow-up, internal notification, manual takeover rule. | Automation Team | Conditional | Medium |  | Not Started
Phase 2 | Payments | Create products/invoice templates if included | Products, invoice template, receipt template, tax settings, payment links, subscription logic if applicable. | Billing | Conditional | High |  | Not Started
Phase 2 | Payments | Build failed payment and billing hold workflows | Failed payment automation, past-due reminders, billing hold, payment hold, refund request workflow, billing task. | Automation Team | Conditional | High |  | Not Started
Phase 2 | Compliance | Build compliance hold workflow | Stops outbound SMS, removes from nurture, creates compliance task, notifies compliance owner, prevents billing/fulfillment triggers where needed. | Automation Team | No | Critical |  | Not Started
Phase 2 | Internal Ops | Build internal task workflows | New lead, callback, no-show, agreement follow-up, missing docs, funding docs, billing issue, compliance review, refund, attorney mention tasks. | Automation Team | No | High |  | Not Started
Phase 2 | Workflow Documentation | Document every workflow | Name, purpose, trigger, conditions, actions, tags applied/removed, fields updated, pipeline movement, exit rules, compliance risks, test status. | Automation Team | No | High |  | Not Started

## PHASE 3 - INTEGRATIONS
PHASE 3 - INTEGRATIONS
Phase | Section | Task | Details / Acceptance Criteria | Owner | Blocker | Priority | Due Date | Status | Document Link | Client Note | Dee's Note | Team's Remarks
Phase 3 | Social Channels | Connect Facebook page if included | Verify access, connect, test inbound messages, route to GHL, apply source tags. | Tech Team | Conditional | Medium |  | Not Started
Phase 3 | Social Channels | Connect Instagram if included | Verify access, connect, test DMs, route social leads, apply source tags. | Tech Team | Conditional | Medium |  | Not Started
Phase 3 | Social Channels | Connect TikTok if included | Connect where supported, document limitations, set source tracking. | Tech Team | Conditional | Low |  | Not Started
Phase 3 | Social Channels | Connect Google Business Profile if included | Connect GBP/GMB, test messaging/reputation features where applicable. | Tech Team | Conditional | Medium |  | Not Started
Phase 3 | ManyChat | Build ManyChat connection if included | Connect ManyChat, map tags/fields, route leads into GHL, booking CTA, keyword triggers, opt-in logic. | Automation Team | Conditional | Medium |  | Not Started
Phase 3 | Reputation | Build review request workflow | Review link, GBP connection, positive review routing, negative feedback internal alert, post-service trigger. | Automation Team | Conditional | Medium |  | Not Started
Phase 3 | Marketing Campaigns | Build lead nurture campaigns | Credit education, funding nurture, commercial funding, clarity, reactivation, DIY product, membership/ebook follow-up as applicable. | Automation Team | Conditional | Medium |  | Not Started
Phase 3 | Marketing Campaigns | Review marketing copy for risk | Remove guarantees, income claims, credit score guarantees, funding guarantees, false urgency, misleading financial promises. | Compliance | Conditional | Critical |  | Not Started
Phase 3 | AI | Configure AI chat if included | AI chat setup, knowledge base, response rules, qualification logic, handoff, fallback, restricted claims list, testing. | Automation Team | Conditional | Medium |  | Not Started
Phase 3 | AI | Test AI compliance guardrails | AI must not give legal/financial advice, guarantee funding/credit outcomes, promise timelines, override holds, or send SMS without consent. | Compliance | Conditional | High |  | Not Started
Phase 3 | Integrations | Build Zapier/Pabbly integrations if included | Configure triggers/actions, field maps, test records, failure alerts, owner/fallback process. | Automation Team | Conditional | High |  | Not Started
Phase 3 | Integrations | Build Google Sheets/Drive storage flows | Lead/client exports, funding tracker, document routing, secure folder links, status updates as included. | Automation Team | Conditional | Medium |  | Not Started
Phase 3 | Integrations | Build DisputeFox data flow if included | Map fields, send lead/client/onboarding info, create internal tasks, store DisputeFox ID, test handoff, document limits. | Automation Team | Conditional | High |  | Not Started
Phase 3 | Integrations | Build Slack/team alerts if included | Route critical internal alerts for leads, docs, billing issues, compliance holds, complaints. | Automation Team | Conditional | Low |  | Not Started
Phase 3 | Tracking | Connect GA4 if included | GA4 installed, page view and conversion events tested. | Tech Team | Conditional | Medium |  | Not Started
Phase 3 | Tracking | Connect Meta/Facebook Pixel if included | Pixel installed, lead/booking/application events tested. | Tech Team | Conditional | Medium |  | Not Started
Phase 3 | Tracking | Configure UTM capture and reporting | UTM source/medium/campaign fields populate and flow into reporting. | Automation Team | No | High |  | Not Started
Phase 3 | Reporting | Build reporting dashboards | Lead source report, speed-to-lead, appointment show rate, revenue, funding status, credit lifecycle, billing issue, compliance hold. | Tech Team | Conditional | Medium |  | Not Started

## PHASE 4 - OPTIMIZATION
PHASE 4 - OPTIMIZATION
Phase | Section | Task | Details / Acceptance Criteria | Owner | Blocker | Priority | Due Date | Status | Document Link | Client Note | Dee's Note | Team's Remarks
Phase 4 | Membership/Portal | Build client portal if included | Client portal/login, resource links, status links, support contact, access rules. | Tech Team | Conditional | Medium |  | Not Started
Phase 4 | Membership/Portal | Build membership/course area if included | Offer, access rule, login page, welcome email, modules, lessons, drip rules, support channel. | Tech Team | Conditional | Medium |  | Not Started
Phase 4 | Digital Products | Build ebook/DIY product delivery if included | Payment trigger, access email, download link, support fallback, failed access workflow. | Automation Team | Conditional | Medium |  | Not Started
Phase 4 | Client Experience | Review lead-to-client journey | Test and optimize entry, booking, agreement, onboarding, funding, credit lifecycle, support, cancellation, complaint paths. | Project Lead | No | High |  | Not Started
Phase 4 | Optimization | Optimize workflow timing | Review wait steps, duplicate notifications, unnecessary alerts, field updates, exit rules. | Automation Team | No | High |  | Not Started
Phase 4 | Optimization | Optimize page/form clarity | Review CTA clarity, form field order, mobile layout, compliance placement, support references. | Tech Team | No | Medium |  | Not Started
Phase 4 | Optimization | Clean tag and field usage | Remove unused/duplicate tags, confirm custom fields are used correctly, no placeholder values live. | Tech Team | No | High |  | Not Started
Phase 4 | Training Prep | Prepare owner/admin training | Dashboard, contacts, pipelines, conversations, calendars, reporting, what not to edit, support process. | Project Lead | No | High |  | Not Started
Phase 4 | Training Prep | Prepare team-role training | Sales, funding advisor, credit specialist, fulfillment, billing, compliance, support, VA training notes. | Project Lead | Conditional | High |  | Not Started
Phase 4 | SOP/Handoff | Prepare system overview | Pipeline guide, workflow guide, form guide, calendar guide, payment guide, integration guide, support process, known limitations. | Project Lead | No | High |  | Not Started
Phase 4 | Support System | Set up 3-month support tracker | Support request categories, priority levels, issue status, owner, response/resolution notes, client updates. | Support | No | High |  | Not Started
Phase 4 | Support System | Define support boundaries | Bug fixes, minor updates, workflow corrections, basic troubleshooting, usage questions included. New builds/major redesigns/custom code/legal review excluded unless approved. | Support | No | High |  | Not Started

## PHASE 5 - QA & DELIVERY
PHASE 5 - QA & DELIVERY
Phase | Section | Task | Details / Acceptance Criteria | Owner | Blocker | Priority | Due Date | Status | Document Link | Client Note | Dee's Note | Team's Remarks
Phase 5 | Website QA | Test all website pages | Home, How It Works, Services, About, FAQ, Schedule, Contact, disclosures, privacy, terms, cancellation, funding pages, 404. | Project Lead | No | Critical |  | Not Started
Phase 5 | Website QA | Test page technical quality | Mobile, desktop, buttons, footer links, SSL, favicon, meta, OG, pixels, GA4, no broken links. | Project Lead | No | Critical |  | Not Started
Phase 5 | Form QA | Test all lead/intake forms | Universal, credit, funding, commercial funding, clarity, onboarding, docs, cancellation, client update, complaint forms. | Project Lead | No | Critical |  | Not Started
Phase 5 | Form QA | Confirm form routing | Contact created, fields updated, tags applied, opportunity created, pipeline/stage correct, owner assigned, notification sent, workflow triggered. | Project Lead | No | Critical |  | Not Started
Phase 5 | Pipeline QA | Test all pipelines | Credit Sales, Credit Active, Funding, Clarity/Education, Support/Risk. Check stages, movement, duplicates, owner, source tracking. | Project Lead | No | Critical |  | Not Started
Phase 5 | Workflow QA | Test lead and appointment workflows | Speed-to-lead, booking confirmation, reminders, no-show, consultation outcome, nurture. | Project Lead | No | Critical |  | Not Started
Phase 5 | Workflow QA | Test agreement/onboarding/credit lifecycle workflows | Agreement sent/signed, cooling-off, manual billing safeguard, onboarding, documents, monitoring, round advancement, cancellation/archive. | Project Lead | Conditional | Critical |  | Not Started
Phase 5 | Workflow QA | Test funding workflows | Document request, docs received, lender submission, terms received, funded, not qualified, nurture. | Project Lead | Conditional | High |  | Not Started
Phase 5 | Communication QA | Test phone and SMS | Inbound/outbound calls, inbound/outbound SMS, voicemail, missed-call text-back, after-hours, STOP, HELP, DND, no-consent block. | Project Lead | Conditional | Critical |  | Not Started
Phase 5 | Communication QA | Test email sending | Gmail, Outlook, reply-to, footer, unsubscribe, suppression, tracking links, spam placement. | Project Lead | Conditional | Critical |  | Not Started
Phase 5 | Compliance QA | Verify compliance guardrails | STOP applies DND, DNC blocks SMS, no-consent SMS blocked, holds stop outbound, cooling-off works, no prohibited claims in pages/templates/AI/voicemail. | Compliance | No | Critical |  | Not Started
Phase 5 | Integration QA | Test integrations | Zapier/Pabbly, DisputeFox, ManyChat, Google Sheets/Drive, Stripe events, Slack/team alerts, social channels, webhooks. | Project Lead | Conditional | High |  | Not Started
Phase 5 | Permission QA | Test role permissions | Admin, Sales, Funding, Credit, Fulfillment, Billing, Compliance, Support, VA. Confirm restrictions and sensitive access controls. | Project Lead | No | High |  | Not Started
Phase 5 | Cleanup | Remove test data and unused assets | Test contacts, opportunities, tags, workflows, draft pages, broken links, placeholder values, duplicate workflows, demo forms, test payments. | Tech Team | No | High |  | Not Started
Phase 5 | Delivery | Prepare final delivery package | Testing log, delivery notes, known limitations, pending approvals, training schedule, walkthrough recording, support handoff, sign-off request, support start date. | Project Lead | No | Critical |  | Not Started
Phase 5 | Training | Deliver user training if scheduled | Owner/admin and team-role training based on selected support/training package. | Project Lead | Conditional | High |  | Not Started
Phase 5 | Go-Live | Client go-live confirmation | Client approves launch readiness, open risks documented, final support window activated. | Agency + Client | No | Critical |  | Not Started